## Sheet1
BACKEND - ADMINISTRATION |  | FRONTEND - USER PERSPECTIVE
http://ec2-52-64-0-243.ap-southeast-2.compute.amazonaws.com/index.php |  | http://ec2-52-64-63-77.ap-southeast-2.compute.amazonaws.com/index.php
Story Ref # | Feature | Story Title | As a/an... | I want to... | So that... | Priority | Estimate (Story Points) | ACCEPTANCE CRITERIA |  | Team 76 - The fighting mongoose notes | TALLY - RELEASE | TALLY - COMPLETED | DATE COMPLETED
1 | Login/Registration | Manager Login | Administrator/Manager | Login to the system | I can continue to maintain the system | Must | 2 | - Manage is able to enter his unique identifier and password to enter the administrative part of the website. | Ben/Steve | How? | 1 | 1 | 2016-09-01
2 | Autonomous confirmation email sending | User Registration Confirmation | Administrator/Manager | Access user information | i may be able to contact students/people enrolled in the course and confirm their booking | Must | 3 | - The manager is able to search through the list of users to email and notify them. | Ben/Steve |  | 1 | 1 | 2016-10-19
3 | Autonomous confirmation email sending | Response for not replying confirmation email | Administrator/Manager | re-open the occupied slot | they can be vacant for other people. | Should | 2 | - The system should remove people who reject or dont reply to the confirmation email two days prior to course commencement and replace them with someone from the waiting list if any exist. The administrator will also have this priveledge. | Ben/Steve | Automatic? | 0 | 0 | 2016-10-20
4 | Database management - Roster Page | Administrator is the boss | Administrator/Manager | have the authority to remove/ban a registered user | i can prevent abuse of and within the system | Should | 4 | - The manager is able to search through a list of users and disable a users account. | Ben/Steve | oversight? | 1 | 1 | 2016-10-03
5 | Database management - Roster Page | Attendance record (Admin priveledge) | Administrator/Manager | be able to check the attendance of staff and student | i can review their performance | Could | 4 | - the manager is able to see the attendance of staff using a gregorian calender | Ben/Steve |  | 1 | 1 | 2016-10-26
6 | Database management - Roster Page | Roles assignment to students | Administrator/Manager | allow old students to be able to serve as a volunteer in a course | they can contribute to the facility and community as a whole | Must | 2 | - Old students are able to apply to a course to work as a voluteer (Server). However, the administrator needs to confirm their application for them to serve. | Ben/Steve | See availabilites of individual volunteers, also automatic? | 1 | 1 | 2016-09-28
7 | Database management - Roster Page | Limitation of the waiting list | Administrator/Manager | there to be a variable limit to the number of people on the waiting list | depending on accomodation we can adjust that value. | Should | 2 | - The system will reject people who want to attend courses after the waiting list is full. | Ben/Steve |  | 1 | 1 | 2016-10-18
8 | Course Creation/Opening | Course Creation/Opening | Administrator/Manager | be able to CREATE courses and OPEN enrolments | Students can participate and know when the couses will start and commence. | Must | 4 | - The administrator has the ability to create a course and set the cemmencement date. after which, users are able to enrol into a course and are emailed 10 days prior to commencement. | Ben/Steve |  | 1 | 1 | 2016-09-22
9 | Notification system | Staff working reminder | Administrator/Manager | be able to notify old students | there is a sufficient number of staff on duty. | Should | 6 | - This is a non-profit organisation and the staff are volunteers, so some days there will be days where there are no volunteers for a course. The administrator is expected to have the ability to send out and email or post an official notice to old students so that volunteers can enrol into a course to serve. | Ben/Steve |  | 1 | 1 | 2016-10-19
11 | Database management - Roster Page | View the Roster | volunteer | view the roster timetable | i can check my working session | Must | 7 | a volunteer can see his working timetable that is generated by system on a particular page. The working session are displayed on a timetable with easy to read writting. | Royce / Brad |  | 1 | 1 | 2016-10-20
13 | Database management - Roster Page | Staff health | Volunteer | I expect that the system has already logged my medical information and allows me to update it | i can be ensured that i will be safe and avoid being hospitalised | Could | 3 | A log of allergies and medical information of every volunteer is stored into a database. A record of all allergies and medical conditions can be seen by the owner. Includes a radial button option for most common allergies and medical condition including the option of 'other'. Small text box to clarify issue. Can be updated whenever the user want. | Royce / Brad |  |  |  | 2016-09-04
14 | Database management - Roster Page | Staff Noticeboards | Volunteer | be able to report course issues or notes to the admin/manager | i can clarify/explain any accident/important issues as a record | Could | 4 | Volunteer can navigate to a page on the website where they can lodge reports. The report has relevant information including time of incident, person reporting and a text box for the nature of the incident. | Royce / Brad | Email? Where does the report go? | 1 | 1 | 2016-10-03
15 | Login/Registration | Member Registration | User of the website | able to register as a student | I can login the system with a unique identifier. | Must | 1 | Provide registration functionality to website. Some fields are optional while others are not (ie. Favourite music is optional while email is not). To be able to become a website member, user need to register in at least one meditation course. | Royce / Brad |  | 1 | 1 | 2016-09-03
16 | donation page | "How to Donate" page | User of the Website | give information to the client how to donate money | i can collect the fund from the client and able to run the center and website | Must | 1 | - There should be a donations page that includes direction on how to donate to the facilty and positively encourages the public to do so. | Royce / Brad |  | 1 | 1 | 2016-09-04
17 | Contact Page | "Contact Us" page | User of the website | able to know how to contact the center | the company can answer any queries i may have with regard to their course/company. | Should | 1 | Create an "About us" page which will display contact info of meditation centre. This page will include a form that the user can fill out. On submission, the form will be emailed to the owner. | Royce / Brad |  | 1 | 1 | 2016-09-15
18 | Database Management - STUDENTS | Medical and allergy information | User of the Website | be able to register my medical information and known allergies | I may be assured safety and can avoid being hospitalised. | Must | 2 | refer to story no. 16 | Royce | is this at a time other than signup? | 1 | 1 | 2016-09-15
19 | HTML/CSS | Course Page | User of the website | able to view the details about the courses | i can gain information of the courses and make the decision to attend or not. | Must | 7 | Create an "Course" page that provides details of courses that the meditation centre provides. This is viewable by all users. The courses can be clicked on to see additional information. | Royce / Brad |  | 1 | 1 | 2016-10-17
20 | ABOUT PAGE | "About" page | User of the website | able to view the introduction to the volunteers and the organisation | I can learn of the facility and service the company offers to the community |  | 1 | - The about page should include a picture of the village, where it is located and the services it provides. | Ben/Steve |  | 1 | 1 | 2016-09-04
21 | HTML/CSS | Website theme | User of the website | be greeted by the website | i can gain insight and a feel for the company. | Should | 3 | For the public and users of the website, it is required that they be greated by cool colours and a calming theme. | Ben/Steve |  | 1 | 1 | 2016-10-13
22 | Login/Registration | Student Login | Registered Student | able to login as a student/volunteer | i can use more functions of the website, e.g. register into courses/ roster | Must | 2 | By using a specifc ID and password, users will be able to login and view content that only registered students and volunteers are allowed to view | Scott |  | 1 | 1 | 2016-09-05
23 | Database Management - STUDENTS | Update Student Profile Page | Registered Student | be able to update my contact details and medical information | i can contact or be contacted in case of emergency. | Should | 2 | The system must remember maintain the medical and allergy information that was logged as a part of the sign up process | Scott | isn't this already there? | 1 | 1 | 2016-09-04
24 | Database Management - STUDENTS | WAITING LIST | Registered Student | be able to register into waiting list if the course is full | i can have a chance to attend the course which i want to join | Should | 3 | When selecting a course to participate in, the user can join the waiting list for a full class, so they may potentially take the spot of someone | Scott | up to seven more poeple | 1 | 1 | 2016-10-16
25 | Database Management - STUDENTS | Attendance confirmation | Registered Student | receive an email which is confirming am i attending the course or not 10 days before the course starts | i can decline the offer if i am not able to attend the course | Should | 6 | Students and Volunteers recieve a email after they register for a course, which they can confirm or decline. | Scott |  | 1 | 1 | 2016-10-20
26 | Database Management - STUDENTS | Student Timetable - Viewing | Registered Student | able to view the course timetable | i can check which course is upcoming and register it | Should | 7 | A student must be easily able to view upcoming course and register into a desired course | Scott |  | 1 | 1 | 2016-09-25
27 | Database Management - STUDENTS | Course upcoming reminder | Registered Student | be notified of the opening of course positions 2 months in advance | i can ENROL in the course and clear my shedule. | Could | 4 | Students Recieve an email a certain amount of time before the course is to begin | Scott | up to?
28 | Registration page | Course Enrolment | Registered Student | Register into the 10 day course using user registration page of the website | open new doorways in my meditation experience | Must | 4 | Only students who have completed 10 day course are able to register easily for a 3 day course | Scott |  | 1 | 1 | 2016-10-03
29 | Change Password | Account Password Changing | Registered Student | Be able to change my password | I am ensured security of my account and my details | Should | 2 | Students once logged in, have access to a account settings page, where they can change their password. | Scott |  | 1 | 1 | 2016-09-26
30 | Autonomous confirmation email sending | Password Recovery | Registered Student | Be sent a verification email to change my password | in case i can recover my account if i forget my password. | Could | 9 | On the off chance that the user forgets his/her password, they click on the forgot password button and they should then enter their email adress. An email is sent, with a link to reset their password. | Teams |  | 1 | 1 | 2016-10-20
31 | Database Management - STUDENTS/STAFF | Volunteer Application | Old Student | be able to volunteer through the website | so I can serve during a course. | Must | 2 | The old student has the ability to open up the roster and apply to work as a volunteer. | Teams |  | 1 | 1 | 2016-09-27
32 | Database Management - STUDENTS/STAFF | Course History | Old Student | be able to provide information of up to last 5 courses that i attended | the facility knows my experience | Could | 2 | The student has an online profile that is stored in the system and on viewing his profile he can see his activity and the courses he has enrolled and completed. | Teams |  | 1 | 1 | 2016-09-30
33 | Database Management - STUDENTS/STAFF | Old Student Course Enrolment | Old Student | Be able to enter a selection of the 3, 10 and 30 day courses | i can continue to build on my knowledge of meditation. | Must | 5 | Old students once completing their 10 day course are able to then reenroll thenselves (If they want) to join either a selection of 3, 10 and 30 day courses | Teams |  | 1 | 1 | 2016-09-29
34 | Database Management - STUDENTS/STAFF | USER PROOFING | Administrator | see that the website is protected from maliscious/unknown code | the integrity of the website is not compromised | MUST | 4 | Upon user registration, user authentification and instances where input values are required, rules and formatting constraints are present to protect the website from maliscious behaviour or otherwise unknown instances that would hinder data integrity or the integrity of the user | Ben/Steve |  | 1 | 1 | 2016-09-13
35 | Database Management - STUDENTS/STAFF | System Testing | Administrator | be assured that across the duration of the project creation, the system has been tested | the integrity of the website is not compromised and the system is reliable. | MUST | 6 | N/A - BACKEND | Ben/Steve |  | 1 | 1 | 2016-10-25
36 | Database Management - STUDENTS/STAFF
37 | DAtabase Management - STUDENTS/STAFF
117
[7 empty] | STORY POINTS |  |  | Sprint 4 | 35 | 0
[10 empty] | Sprint 3 | 22 | 16
[10 empty] | Sprint 2 | 15 | 8
[10 empty] | Sprint 1 | 9 | 4
[11 empty] | Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
[10 empty] | Actual User Stories Remaining | 35 | 31 | 27 | 19 | 0
[10 empty] | Ideal User Stories Remaining | 35 | 26 | 20 | 13 | 0